## Fix Summary
ARAPL_RunILSAnalysis_SR — Fix & Test Summary (Final)
Baldwin Re (Activity 40) and isolated test instruments — full session summary
# | Item | Status | Fix Deployed? | Validated? | Key Finding / Result | Next Step / Owner Ask
0.2 | Company/Industry Loss Minimum fallback | Confirmed Working | Yes | Yes | Every trigger check used Industry Loss Minimum only, ignoring Company Loss Minimum. Fixed to fall back correctly. Verified: 137→133 events, exactly matching the 4 real events below the $75M threshold. | None — closed.
1 | Franchise Deductible | Confirmed Working | Yes | Yes | Relies on fix 0.2. Verified on real Baldwin Re data (layer 345). | None — closed.
2 | Reverse Franchise Deductible | Confirmed Working | Yes | Yes | Ceiling logic was missing entirely from the CATXOL/CATBOND branch. Added combined floor+ceiling check. Verified: surviving losses correctly bounded between $75M and $900M. | None — closed.
3 | Inner Aggregate Deductible | Confirmed Working | Yes | Yes | Verified formula NetNetLoss = max(0, tmpNetLoss − AggregateDeductible) across all 40 non-zero real years, exact match. | None — closed.
4 | Outer Aggregate Deductible | Confirmed Working | Yes | Yes | Verified proportional year-level scaling and full-year exclusion below threshold. Finding: mutually exclusive with Franchise/Reverse Franchise in current code (Outer Aggregate silently disables bits 1/2 if combined). | Flag mutual-exclusivity behavior to owner — confirm if intentional.
5 | Reinstatement Premium waterfall | Confirmed Working | Yes | Yes | Verified all 3 regions of the banded formula (partial band, full band, combined bands) on real data, plus the fully-exhausted ceiling via synthetic multi-event data. | None — closed.
6 | CATBOND unlimited-occurrence-limit cap | Bug Confirmed | Yes (proposed fix) | Mechanically only | Confirmed: with unlimited OccurrenceLimit, modeled loss can exceed the bond's own PrincipalAmount by 2.5x. Fix mechanically correct but not documented anywhere. | Owner sign-off needed before deploying.
7a | RPP — swap mechanism | Confirmed Working | N/A (pre-existing) | Yes | Verified the reinstatement-premium payout correctly swaps in for the RPP container layer and propagates correctly through the inuring chain. | None — closed.
7b | RPP — @ROL rate override | Bug Confirmed | Yes (proposed fix) | Mechanically only | Confirmed: RPP reinstatement premium was unconditionally forced to zero. Fixed; mechanically confirmed. No real RPP structure exists in production to validate against. | Owner input required on LayerPremium's intended source.
8 | AGGTRIGGER (annual ILW) | Confirmed Working | Yes (via 0.2) | Yes | Binary payout mechanic verified on all 140 real years: clean split, no partial values anywhere. | None — closed.
9 | OCCTRIGGER (per-occurrence ILW) | Confirmed Working | Yes (via 0.2) | Yes | Nth-qualifying-event logic verified precisely on the one real year with two qualifying events. | None — closed.
10 | PRORATA | Bug Confirmed, Fix Confirmed Working | Yes | Yes (mechanically) | Confirmed: paid $0 regardless of loss size under StartingEventNumber ≥ 2. Fixed; verified exact arithmetic match across all 140 real years. | Owner sign-off needed — no real data or documentation exists for PRORATA.
11 | OCCILW | Confirmed Working | Yes (via 0.2) | Yes | Both occurrence-capping and proportional scaling verified working correctly together. | None — closed.
12 | Quota Share — Ceded % (cession) | Confirmed Working | Yes | Yes | Redesigned twice during testing to use REAL AIR geography data (GeographySID hierarchy) instead of invented columns. Final design: peril+geography combined into ILSTermsPeril (with optional GeographySID) plus ILSTermsRegion, 4-level priority (peril+place > state > peril > country > treaty default). Tested end-to-end with 5 real-geography events including a genuine non-US fallback case (Japan) — exact match on all 5. | None on the calculation side — this is the most thoroughly validated item in the session. Real TSRe population of the new GeographySID/CededPercent columns is separate, later work (confirmed via the real ARAPL_populate_ILSTerms source that QS_Cession is currently hardcoded NULL there).
13 | Coinsurance | Confirmed Working | Yes | Yes | Direction confirmed directly (CoinsuranceAmount = cedant's retained share). Applied to both Loss and NetLoss_xRIP, tested exact. A serious deployment mistake (an accidentally-deleted EXECUTE line, which would have zeroed EVERY layer's output) was caught immediately and corrected. | None — closed on the calculation side. Real-data question (Baldwin Re's CoinsuranceAmount matching ParticipationGross) remains separately deferred.
14 | ELSE catch-all / GU layers | Confirmed Working | N/A | Yes | The ELSE pass-through logic confirmed correct. Real ARAPL_populate_ILSTerms source later confirmed GU layers' ParentRelationType=3 is a genuine 'sourced, deeper inuring level' case, not an anomaly. Synthetic test proved the GU/CATBOND mechanism works correctly end-to-end. | Verify against the full production environment whether GU layers for ~25 real instruments have real loss-set associations.
15 | Drop-Down Cover | Confirmed Working | Yes | Yes | StepLayerSequenceNumber was never wired anywhere — confirmed via the real ARAPL_populate_ILSTerms source that ParentRelationType can only ever be 1/2/3 from real conversions, meaning no real Drop-Down structure can exist via the standard TSRe path today. Built new engine-side wiring and tested against AIR's own documented 4-event worked example — exact match. | Separate, larger fix needed: add StepLayerSequenceNumber to production ILSTerms and update ARAPL_populate_ILSTerms to carry it from TSRe.
— | Multi-child sourcing/inuring at one parent (structural) | Confirmed Working | N/A (pre-existing) | Yes | Built a CATBOND parent with 3 CATXOL children (2 sourced, 1 inuring). Confirmed the underlying-layers loop correctly combines ALL children, and each child's own sourced/inuring behavior applies independently. | None — closed. Multiple STEP-LAYER tiers (3+) in a single Drop-Down chain remain unconfirmed/unsupported.

## Open Items
Open / Pending Items — Not Yet Actioned
• Three confirmed bugs (items 6, 7b, 10) have mechanically-tested fixes ready, but each needs product/business sign-off before deployment — none have real production data or documentation to validate the business assumption against.
• Item 12's real-data pipeline: the actual ARAPL_populate_ILSTerms source was obtained and reviewed this engagement — confirmed QS_Cession is explicitly hardcoded to NULL, and CededPercent is available but unused in an existing join. Wiring real TSRe cession data into the new ILSTermsRegion/ILSTermsPeril columns is separate, later work; only the calculation-engine side was built and tested this engagement.
• Item 12's priority ordering (peril beats a plain country-level rule) was informed by AIR's own PerilRegion data structure and general market convention, not a document-confirmed rule for this business's own treaties — worth final confirmation from whoever structures real treaties.
• Item 15 (Drop-Down Cover): the real ARAPL_populate_ILSTerms source confirms ParentRelationType can only ever be 1/2/3 from a standard TSRe conversion — meaning no real Drop-Down structure (which needs ParentRelationType=5) can exist today without a separate, unseen entry process. The fix itself is validated against AIR's documentation but needs a larger upstream schema/conversion fix before any real deal can reach it.
• GU layer / loss-data completeness (item 14) needs to be checked against the real production environment, not this working test database, before treating it as a genuine gap.
• Multiple step-layer tiers (3+) in a single Drop-Down Cover chain are NOT supported by the current fix — only one primary + one step-layer has been built and tested.
• Item 13's real-data question (Baldwin Re's CoinsuranceAmount values suspiciously matching ParticipationGross) remains deferred and uninvestigated — the calculation logic itself is confirmed correct regardless.
• A serious deployment mistake was caught during item 13's testing: an edit accidentally deleted the line that executes each layer's final output query, which would have silently zeroed every layer's output of every type. Caught immediately via the very next test — worth spot-re-verifying one earlier 'confirmed' item for extra assurance, though the risk window is assessed as very unlikely to have overlapped any prior test.
• The real ARAPL_populate_ILSTerms source (obtained and reviewed late in this engagement) independently confirmed every previously document-inferred population gap (DeductibleType, AggregateDeductible, LayerPremium, StepLayerSequenceNumber all absent from the real ~55-column INSERT list) — none of this changes any fix or test already completed, since these are all downstream inputs to the calculation engine, not the calculation logic itself.
• Test instruments, layers, and synthetic loss sets created throughout this engagement (isolated test instruments 338-348 and their layers, plus TEST_SummaryIndustryLoss_Stoch_Final and its v2 successor) still exist in the working database — decide on cleanup vs. retention. The now-superseded ILSTermsCessionRules table (Phase 14's original cession design) can likely be dropped.
• Layers 344 and 346 (real Baldwin Re CATBOND/CATXOL layers) have NO loss-set association at all — a real data-quality issue discovered early in testing, separate from anything in this fix list, never resolved.
• Downstream dependency arapl_GetRemainingAAL (called at the end of the main procedure) has never been reviewed — its own required inputs and correctness are unknown.